## Summary
| Total Acres | 5228.3766 | Total Acres Picked |  | 1838.7201 | 35.17% | Total Acres In Progress |  | 122.66 | 2.346% |  |  | Total Acres Pending |  | 3053.2465 | 58.4%
| Clements Acres | 1992.3565 | [5 empty] | Delta Acres | 1323.11 | [5 empty] | Lodi Acres | 1912.9101
| Picked | 384.98 | 19.32% |  |  |  |  | Picked | 884.5 | 66.85% |  |  |  |  | Picked | 569.2401 | 29.76%
| In Progress | 65.83 | 3.304% |  |  |  |  | In Progress | 9.28 | 0.7014% |  |  |  |  | In Progress | 47.55 | 2.486%
| Pending | 1536.5465 | 77.12% |  |  |  |  | Pending | 224.53 | 16.97% |  |  |  |  | Pending | 1292.17 | 67.55%
| No/Maybe Pick | 5 | 0.251% |  |  |  |  | No/Maybe Pick | 202.68 | 15.32% |  |  |  |  | No/Maybe Pick | 3.95 | 0.2065%
CLEMENTS | [6 empty] | DELTA | [6 empty] | LODI
CODE | ACRES | AC. LEFT | FINISHED | TONS | TPA |  | CODE | ACRES | AC. LEFT | FINISHED | TONS | TPA |  | CODE | ACRES | AC. LEFT | FINISHED | TONS | TPA
98OK01CS | 22.9457 | 22.9457 | 0 |  |  |  | DVDU02SB | 39.42 | 0 | 39.42 |  |  |  | ARDA01CS | 36.81 | 36.81 | 0
98OK02CS | 15.9107 | 15.9107 | 0 |  |  |  | DVDU05CH | 42.04 | 0 | 42.04 |  |  |  | BAPE01CH | 42.1201 | 0 | 42.1201 |  | 0
98OK03MA | 19.0519 | 19.0519 | 0 |  |  |  | DVDU07MC | 28.51 | 0.5 | 28.01 |  |  |  | BEBU01ME | 46.96 | 0 | 46.96 |  | 0
98OK04CS | 26.5256 | 26.5256 | 0 |  |  |  | DVDU1CSB | 45.21 | 0 | 45.21 |  |  |  | DBAI02SA | 10.03 | 10.03 | 0
98OK05CS | 20.2326 | 20.2326 | 0 |  |  |  | DVMA01PN | 46.69 | 0 | 46.69 |  |  |  | DBAI03ZN | 9.27 | 0 | 9.27
98OK06CS | 24.5 | 24.5 | 0 |  |  |  | DVMA02PG | 102.93 | 0 | 102.93 |  |  |  | DBAI04CS | 9.27 | 9.27 | 0
98OK07ME | 37.6 | 24.62 | 12.98 |  |  |  | FFRY01PN | 38.21 | 0.33 | 37.88 |  |  |  | DBDA05CH | 10.07 | 10.07 | 0
98OK08PS | 24.5 | 24.5 | 0 |  |  |  | FFRY02PN | 15.18 | 15.18 | 0 |  |  |  | DFDA04ZN | 8.07 | 0 | 8.07 |  | 0
98OK09CS | 39.2 | 39.2 | 0 |  |  |  | FFRY04CH | 15.95 | 0.71 | 15.24 |  |  |  | DFDA07ND | 6.72 | 0.29 | 6.43 |  | 0
98OK10ZN | 18.8 | 18.8 | 0 |  |  |  | FFRY05CH | 24.82 | 0.91 | 23.91 |  |  |  | FDJA01TO | 20.25 | 20.25 | 0
98OK11CF | 21 | 21 | 0 |  |  |  | FFRY09PN | 4.53 | 4.53 | 0 |  |  |  | FDJA02TE | 20.26 | 20.26 | 0
BAVC01ZN | 17.14 | 17.14 | 0 |  |  |  | FFRY10PN | 9.48 | 9.48 | 0 |  |  |  | FDJA03MA | 36.25 | 36.25 | 0
BAVC02PR | 11.79 | 11.79 | 0 |  |  |  | FFRY15CB | 41.01 | 41.01 | 0 |  |  |  | FDJA04ME | 41.1 | 41.1 | 0
BHCH01CS | 45.32 | 45.32 | 0 |  |  |  | FFRY3BXX | 19.96 | 19.96 | 0 |  |  |  | FDJA05ME | 18.39 | 18.39 | 0
BSHMOHCS | 5 | 5 | 0 |  |  |  | FFRY99PN | 18.11 | 18.11 | 0 |  |  |  | FRDU01ME | 3.73 | 3.73 | 0
CL3A02SB | 50.74 | 0 | 50.74 |  |  |  | MFRN00PN | 5 | 5 | 0 |  |  |  | HEBO01CS | 17.14 | 17.14 | 0
CLAT05CS | 34.92 | 34.92 | 0 |  |  |  | MFRN02PN | 45.71 | 23.75 | 21.96 |  |  |  | HIHV04CS | 44.56 | 44.56 | 0
CLBC00VD | 7.1 | 7.1 | 0 |  |  |  | MFRN03PG | 45.11 | 0 | 45.11 |  |  |  | HIHV05PS | 57.07 | 57.07 | 0
CLBC01PG | 39.34 | 0 | 39.34 | 264 | 6.7107 |  | MJMJ02PG | 66.53 | 0 | 66.53 |  |  |  | IWHM01CS | 3.95 | 3.95 | 0
CLBC02CH | 59.54 | 59.54 | 0 |  |  |  | MJMJ03CB | 19.38 | 0 | 19.38 |  |  |  | JONR01CH | 37.82 | 0 | 37.82 |  | 0
CLLA01ME | 72.66 | 72.66 | 0 |  |  |  | MJMJ04CB | 36.77 | 6.78 | 29.99 |  |  |  | JONR02SB | 7.06 | 0 | 7.06 |  | 0
CLMN01SY | 60.52 | 0 | 60.52 |  |  |  | ONMI01CS | 36.13 | 36.13 | 0 |  |  |  | JONR03GV | 4.51 | 4.51 | 0
CLMN03PS | 4.97 | 4.97 | 0 |  |  |  | ONMI02CS | 41.4 | 41.4 | 0 |  |  |  | LAPR02CH | 34.2 | 34.2 | 0
CLMN04PS | 12.29 | 12.29 | 0 |  |  |  | ONMI04CS | 30.18 | 30.18 | 0 |  |  |  | LAPR03ME | 34.06 | 34.06 | 0
CLMN05PS | 16.22 | 16.22 | 0 |  |  |  | ONMI05CS | 32.99 | 32.99 | 0 |  |  |  | LAPR04PS | 43.76 | 43.76 | 0
CLMO01BA | 34.41 | 0 | 34.41 |  |  |  | ONMI06CS | 30.71 | 30.71 | 0 |  |  |  | LAPR05CS | 43.1 | 43.1 | 0
CLNR01CS | 59.72 | 59.72 | 0 |  |  |  | ONMI07ME | 38.76 | 0 | 38.76 |  |  |  | LF1001CS | 49.01 | 49.01 | 0
CLOK02CS | 104.19 | 104.19 | 0 |  |  |  | ONMI08ME | 38.34 | 0 | 38.34 |  |  |  | LF1002PS | 49.52 | 49.52 | 0
CLOK1AME | 50.38 | 50.38 | 0 |  |  |  | ONMI09CH | 39.13 | 0 | 39.13 |  |  |  | LF3801CS | 48.52 | 48.52 | 0
CLPC02BA | 28.07 | 11.58 | 16.49 |  |  |  | ONMI3ACS | 8.77 | 8.77 | 0 |  |  |  | LF8001TD | 24.87 | 24.87 | 0
CLPC07CS | 86.1 | 86.1 | 0 |  |  |  | ONMI3BCS | 25.73 | 25.73 | 0 |  |  |  | LF8004CH | 18.48 | 0 | 18.48
CLPC3BME | 43.28 | 43.28 | 0 |  |  |  | PRHZ01CH | 12.58 | 0 | 12.58 |  |  |  | LFBE01CS | 58.08 | 58.08 | 0
CLPC4APR | 57.99 | 57.99 | 0 |  |  |  | PRHZ02PN | 7.27 | 0 | 7.27 |  |  |  | LFBE02VI | 38.38 | 0 | 38.38
CLPC4BCH | 60.57 | 60.57 | 0 |  |  |  | PRHZ03PN | 7.06 | 0 | 7.06 |  |  |  | LFBT01CH | 37.34 | 0 | 37.34
CLPT01CS | 83.51 | 83.51 | 0 |  |  |  | PRHZ09SB | 13.77 | 13.77 | 0 |  |  |  | LFBT02SB | 37.45 | 0 | 37.45
CLR201MA | 35.56 | 35.56 | 0 |  |  |  | PRHZ10SB | 4.93 | 4.93 | 0 |  |  |  | LFDA02PG | 9.75 | 0 | 9.75
CLR202CH | 70.35 | 70.35 | 0 |  |  |  | PRHZ11CB | 19.86 | 0 | 19.86 |  |  |  | LFEX01SA | 16.87 | 12.83 | 4.04
GEWENOCH | 26.24 | 26.24 | 0 |  |  |  | PRHZ12CH | 10 | 10 | 0 |  |  |  | LFEX02SY | 19.71 | 19.71 | 0
KBBR01ZN | 29.27 | 29.27 | 0 |  |  |  | PRHZ13PG | 17.81 | 17.81 | 0 |  |  |  | LFEX03VI | 16.13 | 0 | 16.13 |  | 0
KBBR02TD | 22.59 | 22.59 | 0 |  |  |  | PRHZ14CB | 3.03 | 0 | 3.03 |  |  |  | LFEX04VI | 11.78 | 0 | 11.78 |  | 0
MFLO01PG | 42.4 | 0 | 42.4 |  |  |  | PRHZ15CB | 22.93 | 0 | 22.93 |  |  |  | LFGC01CS | 83.49 | 83.49 | 0
MFLO02TE | 22.37 | 22.37 | 0 |  |  |  | PRHZ16CB | 6.52 | 2.5 | 4.02 |  |  |  | LFRA02CF | 14.91 | 14.91 | 0
MRPR01CS | 35.04 | 35.04 | 0 |  |  |  | PRHZ17CB | 7.28 | 0 | 7.28 |  |  |  | LFRR02CS | 11.29 | 11.29 | 0
POCR03CS | 59.66 | 59.66 | 0 |  |  |  | PRHZ18PS | 9.55 | 9.55 | 0 |  |  |  | LFRR03CS | 29.38 | 29.38 | 0
POHM01PV | 15 | 15 | 0 |  |  |  | PRHZ19BM | [6 empty] | LFRR04CS | 8.48 | 8.48 | 0
PPBR03CH | 41.7 | 0 | 41.7 |  |  |  | PRHZ20OM | 18.82 | 18.82 | 0 |  |  |  | LFRR05MP | 4.69 | 4.69 | 0
PPCR01ME | 34.08 | 34.08 | 0 |  |  |  | PRHZ21CH | 9.75 | 0 | 9.75 |  |  |  | LFRR06AG | 6.75 | 6.75 | 0
PPCR02CH | 32.79 | 0 | 32.79 |  |  |  | PRHZ22CB | 3.85 | 0 | 3.85 |  |  |  | LFRR07PB | 5.05 | 5.05 | 0
RSR101CH | 27.32 | 27.32 | 0 |  |  |  | PRHZ99MA | 9.07 | 9.07 | 0 |  |  |  | LFRR08GB | 4.75 | 0 | 4.75 |  | 0
RSR103CH | 8.84 | 8.84 | 0 |  |  |  | PRHZ99VV | 2.87 | 0 | 2.87 |  |  |  | LFRT02PR | 27.8 | 14.72 | 13.08 |  | 0
SMSM01ME | 23.13 | 23.13 | 0 |  |  |  | WHWH01GE | 38.4 | 0 | 38.4 |  |  |  | LFRT03AN | 0.33 | 0 | 0.33 |  | 0
SZVC01ZN | 10.65 | 10.65 | 0 |  |  |  | WHWH02PG | 34.89 | 0 | 34.89 |  |  |  | LFTO01CS | 57.29 | 57.29 | 0
SZVC02ZN | 12.09 | 12.09 | 0 |  |  |  | WHWH03AL | 30.18 | 0 | 30.18 |  |  |  | LFTO02SB | 56.02 | 0 | 56.02 |  | 0
ZLLAOHCS | 44 | 44 | 0 | [10 empty] | LFW104CS | 54.49 | 54.49 | 0
ZLSO01PN | 83.24 | 29.63 | 53.61 | [10 empty] | LFW105CH | 17.33 | 0 | 17.33 |  | 0
[14 empty] | LFW106KU | 2.5 | 2.5 | 0
[14 empty] | LFW301CS | 40.39 | 40.39 | 0
[14 empty] | MEJA03CS | 31.12 | 31.12 | 0
[14 empty] | MKJA04CS | 36.41 | 36.41 | 0
[14 empty] | MUMU01SB | 21.38 | 0 | 21.38 |  | 0
[14 empty] | MUMU02PG | 20.98 | 0 | 20.98 |  | 0
[14 empty] | MVDU01CS | 4.08 | 4.08 | 0
[14 empty] | MVDU02ME | 8.38 | 8.38 | 0
[14 empty] | RING01CS | 64.31 | 64.31 | 0
[14 empty] | SEJA01CS | 18.59 | 18.59 | 0
[14 empty] | SLHM01TD | 19.55 | 19.55 | 0
[14 empty] | SLHM02VI | 19.35 | 0 | 19.35 |  | 0
[14 empty] | SLHM03CH | 19.13 | 19.13 | 0
[14 empty] | SLHM04SB | 35.5 | 0 | 35.5 |  | 0
[14 empty] | SLHM05PN | 23.24 | 0 | 23.24 |  | 0
[14 empty] | SLHM06ZN | 4.72 | 4.72 | 0
[14 empty] | SLHM08PR | 7.16 | 7.16 | 0
[14 empty] | SZDU01CH | 22.58 | 22.58 | 0
[14 empty] | SZDU02ZN | 22.87 | 22.87 | 0
[14 empty] | VKDD01CH | 26.2 | 0 | 26.2 |  | 0
Note on K59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.32 acres left in the field not picking

## Row Counts
REMINDER: FILTER ONLY - DO NOT SORT!
DATE | BLOCK | VINE SPACING | TOTAL VINES | VINES PICKED | VINES LEFT | TOTAL ACRES | ACRES PICKED | ACRES LEFT | ACRES PICKED SINCE LAST COUNT | LOADS | WINERY | TONS PICKED TODAY | TPA | LOADS TO FINISH | ROW COUNT REPORTED BY | ROWS | NOTES
2026-07-15 | LF8004CH | 622 | 11433 | 5585 | 5848 | 18.381 | 8.9791 | 9.4019 | 8.9791 | 2.5 | LTW | 53.55 | 5.9638 | 2.4379 | Luis | Picked: 24-45 (Rosa FC)
2026-07-21 | LFEX01SA | 605 | 10120 | 2356 | 7764 | 16.7273 | 3.8942 | 12.8331 | 3.8942 | 1 | LTW | 24.43 | 6.2734 | 3.5003 | Luis | Picked: 8-23,25,27,39(1/2)
2026-07-21 | DBAI03ZN | 622 | 5633 | 2629 | 3004 | 9.0563 | 4.2267 | 4.8296 | 4.2267 | 1 | LTW | 24.37 | 5.7657 | 1.2107 | Luis | Picked: 6-41,43,45,47(25vines)
2026-07-23 | CLBC01PG | 681 | 26421 | 13699 | 12722 | 38.7974 | 20.116 | 18.6814 | 20.116 | 6 | Oneill | 142.24 | 7.071 | 5.7433 | Luis | Picked: 1-34,36-48,50,52,54,56,65,67,69-72-74,76, Row 56 is 3/4 picked, Row 73 is 1/2 picked. We estimated for unknowns
2026-07-24 | CLBC01PG | 681 | 26421 | 26421 | 0 | 38.7974 | 38.7974 | 0 | 18.6814 | 5.25 | Oneill | 122.51 | 6.5579 | 0 | Luis | FC
2026-07-27 | DVDU1CSB | 726 | 32514 | 13022 | 19492 | 44.7851 | 17.9366 | 26.8485 | 17.9366 | 6 | Gallo | 134.45 | 7.4958 | 8.7501 | Luis | Left to pick: 9,13,15,24,26,28-40,48,50,52-81, row 24 1/2 picked, row 15 1/4 picked, row 48 3/4 picked
2026-07-27 | LFEX01SA | 605 | 10120 | 6532 | 3588 | 16.7273 | 10.7967 | 5.9306 | 10.7967 | 2 | LTW | 51.27 | 4.7487 | 1.2245 | Kyle | Picked rows: 8-55, 56(1/2), 57, 59, 61(1/2)
2026-07-27 | MUMU02PG | 681 | 14141 | 8916 | 5225 | 20.7651 | 13.0925 | 7.6725 | 13.0925 | 3 | Fetzer | 69.71 | 5.3244 | 1.7762 | Luis | Left to pick: 1-17,19,21,24-37,39,41,
2026-07-28 | DVDU1CSB | 726 | 32514 | 27282 | 5232 | 44.7851 | 37.5785 | 7.2066 | 19.6419 | 7 | Gallo | 156.16 | 7.9504 | 2.4911 | Luis | Left to pick: 36,38,40,68,70-74,76-77,79-81, row 36 is 1/2 picked, row 76 is 1/2 picked
2026-07-28 | DVMA02PG | 908 | 94178 | 24105 | 70073 | 103.7203 | 26.5474 | 77.1729 | 26.5474 | 6 | LTW | 142.24 | 5.358 | 17.9778 | Mat | picked: 215-295,298(1/2W),299-323,344,346-365,367,374-378,381,383,385,387
2026-07-28 | MUMU02PG | 681 | 14141 | 14141 | 0 | 20.7651 | 20.7651 | 0 | 7.6725 | 1.75 | Fetzer | 39.56 | 5.156 | 0 | Luis | FC
2026-07-29 | DVDU1CSB | 726 | 32514 | 32514 | 0 | 44.7851 | 44.7851 | 0 | 7.2066 | 2.25 | Gallo | 51.08 | 7.0879 | 0 | Luis | FC
2026-07-29 | DVDU02SB | 726 | 28200 | 9610 | 18590 | 38.843 | 13.2369 | 25.6061 | 13.2369 | 5.75 | Gallo | 131.02 | 9.8981 | 11.0196 | Luis | Left to pick: 1-30,31,33,40,42-47,49,52,59-67,70, | 2.25 loads other 3 gondolas came out of Block 2 to fill load 3
2026-07-29 | JONR02SB | 726 | 4941 | 4941 | 0 | 6.8058 | 6.8058 | 0 | 6.8058 | 2.5 | Delicato | 55.8 | 8.1989 | 0 | Luis | FC
2026-07-30 | DVDU02SB | 726 | 28200 | 27120 | 1080 | 38.843 | 37.3554 | 1.4876 | 24.1185 | 9 | Gallo | 210.79 | 8.7398 | 0.56527 | Luis | Left to pick: 8,12,17,19 rows 12 and 19 halfway picked
2026-07-30 | MUMU01SB | 605 | 12811 | 9035 | 3776 | 21.1752 | 14.9339 | 6.2413 | 14.9339 | 4 | Fetzer | 91.73 | 6.1424 | 1.6668 | Luis | Left to pick: 61,63,65-71,73-92, row 71 is 1/2 picked row 61 is 1/2 picked
2026-07-30 | LFEX03VI | 605 | 9777 | 6926 | 2851 | 16.1603 | 11.4479 | 4.7124 | 11.4479 | 2.25 | LTW-Pine | 55.51 | 4.8489 | 0.99348 | Luis | Left to pick: 91-94,115-138, rows 115-138 only picked on the West side
2026-07-30 | LFEX04VI | 778 | 9125 | 8663 | 462 | 11.7288 | 11.135 | 0.59383 | 11.135 | 1.75 | LTW-Pine | 45.86 | 4.1186 | 0.10634 | Luis | Left to pick: 1,52-53,
2026-07-31 | DVDU02SB | 726 | 28200 | 28200 | 0 | 38.843 | 38.843 | 0 | 1.4876 | 0.5 | Gallo | 11.15 | 7.4953 | 0 | Mat | FC
2026-07-31 | WHWH01GE | 691 | 26251 | 14439 | 11812 | 37.9899 | 20.8958 | 17.0941 | 20.8958 | 6.5 | LTW | 152.71 | 7.3082 | 5.4316 | Mat | Picked 1-79
2026-07-31 | LFEX03VI | 605 | 9777 | 9777 | 0 | 16.1603 | 16.1603 | 0 | 4.7124 |  | LTW-Pine | 12.69 | 2.6929 | 0 | Luis | FC
2026-07-31 | LFEX04VI | 778 | 9125 | 9125 | 0 | 11.7288 | 11.7288 | 0 | 0.59383 |  | LTW-Pine | 4.23 | 7.1232 | 0 | Luis | FC
2026-07-31 | SLHM04SB | 622 | 21904 | 14787 | 7117 | 35.2154 | 23.7733 | 11.4421 | 23.7733 | 6 | LTW | 140.55 | 5.9121 | 2.9412 | Luis | East left to pick: 43-45,48-55,58-78,West left to pick: 41-72,83
2026-07-31 | MUMU01SB | 605 | 12811 | 12811 | 0 | 21.1752 | 21.1752 | 0 | 6.2413 | 1.75 | Fetzer | 34.51 | 5.5293 | 0 | Luis | FC
2026-07-31 | LFDA02PG | 908 | 8809 | 8809 | 0 | 9.7015 | 9.7015 | 0 | 9.7015 | 2.25 | LTW | 51.04 | 5.261 | 0 | Luis | FC
2026-08-03 | DVMA02PG | 908 | 94178 | 50507 | 43671 | 103.7203 | 55.6244 | 48.0958 | 29.0771 | 7 | Delicato | 167.38 | 5.7564 | 12.0374 | Leonardo | left to pick: 42,44-170,172,386,388,390-466,468,470 | May have some half rows that are actually picked in there
2026-08-03 | SLHM04SB | 622 | 21904 | 21904 | 0 | 35.2154 | 35.2154 | 0 | 11.4421 | 2.75 | LTW | 65.29 | 5.7061 | 0 | Mat | FC
2026-08-03 | SLHM02VI | 605 | 11526 | 11526 | 0 | 19.0512 | 19.0512 | 0 | 19.0512 | 4 | LTW | 93.64 | 4.9152 | 0 | Mat | FC
2026-08-03 | MFRN03PG | 807 | 36108 | 14077 | 22031 | 44.7435 | 17.4436 | 27.2999 | 17.4436 | 6 | Gallo | 143.86 | 8.2471 | 9.789 | Luis | Left to pick: 32,34-124,126,147-148,150, rows 35,147 half picked
2026-08-04 | DVMA01PN | 691 | 30586 | 5676 | 24910 | 44.2634 | 8.2142 | 36.0492 | 8.2142 | 3 | LTW | 70.09 | 8.5328 | 13.3739 | Luis | EAST left to pick 55-50,48,36,34-33,31-30,28,5,1, Row 30 is 3/4 picked
2026-08-04 | DVMA02PG | 908 | 94178 | 63517 | 30661 | 103.7203 | 69.9526 | 33.7676 | 14.3282 | 4 | Delicato | 93.58 | 6.5312 | 9.5888 | Leonardo | Left to pick: 60,62,64,65(1/2),66-146,148,386,388,390-448,450
2026-08-04 | PRHZ02PN | 691 | 4869 | 4869 | 0 | 7.0463 | 7.0463 | 0 | 7.0463 | 1 | LTW-KOSHER | 37.35 | 5.3006 | 0 | Mat | FC - 1 hand pick load and 2.5 gondolas
2026-08-04 | PRHZ03PN | 691 | 4876 | 2476 | 2400 | 7.0564 | 3.5832 | 3.4732 | 3.5832 | 1.5 | LTW-KOSHER | 16.27 | 4.5406 | 0.68568 | Mat | Left to pick: 76-105 3.25 gondolas ¦ 1 hand load and 1.5 machine loads
2026-08-04 | WHWH01GE | 691 | 26251 | 26251 | 0 | 37.9899 | 37.9899 | 0 | 17.0941 | 3.25 | TWG-WDBG | 77.77 | 4.5495 | 0 | Luis | FC
2026-08-04 | LFBT02SB | 726 | 27203 | 20338 | 6865 | 37.4697 | 28.0138 | 9.4559 | 28.0138 | 8 | LTW | 191.92 | 3 | 1.2334 | Kyle | left to pick: 66(1/2 east), 70-74, 91, 93, 94(1/2 W), 95-99, 114, 118-159
2026-08-04 | MFRN03PG | 807 | 36108 | 30971 | 5137 | 44.7435 | 38.3779 | 6.3656 | 20.9343 | 7 | Gallo | 167.74 | 8.0127 | 2.2176 | Abel | left to pick: 65,67,68(1/2),69-86,89,91(1/2)
2026-08-05 | DVMA02PG | 908 | 94178 | 87308 | 6870 | 103.7203 | 96.1542 | 7.5661 | 26.2015 | 7 | Delicato | 163.02 | 6.2218 | 2.0467 | Luis | Left to pick: 102-107,109,111,386,388,390-413,415, row 102 (54 unpicked) row 412 (51 unpicked)
2026-08-05 | MFRN03PG | 807 | 36108 | 36108 | 0 | 44.7435 | 44.7435 | 0 | 6.3656 | 2.5 | Gallo | 57.08 | 8.967 | 0 | Luis | FC
2026-08-05 | PRHZ03PN | 691 | 4876 |  | 0 | 7.0564 | 0 | 0 | 0 | 0.75 | LTW-KOSHER | 16.13 | 0 |  | Luis | FC
2026-08-05 | DVDU07MC | 545 | 15354 | 5401 | 9953 | 28.1725 | 9.9101 | 18.2624 | 9.9101 | 2 | LTW | 49.04 | 4.9485 | 3.9292 | Luis | Picked: 20-38 (rows 35-38 half picked) 1-4 half picked
2026-08-05 | MFLO01PG | 908 | 37921 | 17377 | 20544 | 41.7632 | 19.1377 | 22.6256 | 19.1377 | 4.5 | Sutter Home - St Helena | 98.31 | 5.137 | 5.0534 | Mat | picked: 123-213
2026-08-05 | DBAI03ZN | 622 | 5633 | 5633 | 0 | 9.0563 | 9.0563 | 0 | 4.8296 | 1 | LTW | 21.75 | 4.5035 | 0 | Mat | FC
2026-08-05 | LFRT02PR | 691 | 18780 | 8609 | 10171 | 27.178 | 12.4588 | 14.7192 | 12.4588 | 4 | LTW | 95.32 | 7.6508 | 4.8963 | Mat | picked All of West block. East block: 1-22,24,26,30,32-50
2026-08-05 | LFBT02SB | 726 | 27203 | 27203 | 0 | 37.4697 | 37.4697 | 0 | 9.4559 | 2.5 | LTW | 61.81 | 6.5366 | 0 | Mat | FC
2026-08-06 | LFBT01CH | 807 | 30338 | 30338 | 0 | 37.5936 | 37.5936 | 0 | 37.5936 | 8 | LTW | 193.49 | 5.1469 | 0 | Mat | FC
2026-08-06 | MJMJ02PG | 691 | 45595 | 18487 | 27108 | 65.9841 | 26.754 | 39.2301 | 26.754 | 7 | LTW | 164.93 | 6.1647 | 10.5148 | Mat | Picked: 1-85,87-93,95
2026-08-06 | MJMJ02PG-old | 691 | 30372 |  | 0 | 43.9537 | 0 | 0 | 0 |  | LTW | 0 | 0
2026-08-06 | MJMJ02PG-retrain | 691 | 15223 | 15223 | 0 | 22.0304 | 22.0304 | 0 | 22.0304 |  | LTW | 0 | 0 | 0
2026-08-06 | DVMA01PN | 691 | 30586 | 18376 | 12210 | 44.2634 | 26.5933 | 17.67 | 18.3792 | 5.5 | LTW | 125.73 | 6.8409 | 5.2556 | Mat | West unpicked: 14-17,33,50,52-54-63,67-101, row 53 and 69 are 3/4 picked
2026-08-06 | MFRN02PN | 807 | 36610 | 17447 | 19163 | 45.3656 | 21.6196 | 23.746 | 21.6196 | 7 | LTW | 167.2 | 7.7337 | 7.9846 | Mat | Picked: 71-95,97,99-124,126-142,144,146,147,150
2026-08-06 | DVMA02PG | 908 | 94178 | 94178 | 0 | 103.7203 | 103.7203 | 0 | 103.7203 | 2 | Delicato | 47.12 | 0.4543 | 0 | Mat | FC
2026-08-06 | MFLO01PG | 908 | 37921 | 30132 | 7789 | 41.7632 | 33.185 | 8.5782 | 14.0474 | 4 | Gallo-J Winery | 92.11 | 6.5571 | 2.4456 |  | left to pick rows 90-122 plus 1068 vines in rows 70-89.
2026-08-06 | JONR01CH | 605 | 22654 |  | 0 | 37.4446 | 0 | 0 | 0 |  | Estate Crush | 5.13 | 0
2026-08-06 | DVDU07MC | 545 | 15354 | 15081 | 273 | 28.1725 | 27.6716 | 0.50092 | 17.7615 | 4 | LTW | 95.6 | 5.3824 | 0.11722
2026-08-07 | DVMA01PN | 691 | 30586 | 30586 | 0 | 44.2634 | 44.2634 | 0 | 44.2634 | 5.75 | LTW | 136.72 | 3.0888 | 0 | Mat | FC
2026-08-07 | MJMJ02PG | 691 | 30586 | 16380 | 14206 | 44.2634 | 23.7048 | 20.5586 | 18.6715 | 4 | LTW | 94.47 | 5.0596 | 4.5225 | Kyle | left to pick: 116(1/2), 117-118, 150, 152, 154, 156-280. | Mineral weak section - remaining TPA will be higher!
2026-08-07 | LFBE02VI | 778 | 29280 | 29280 | 0 | 37.635 | 26.34 | 11.295 | 26.34 | 3 | LTW -Pine | 72.01 | 2.7339 | 1.3426 |  | FC | This total tonnage is just pine ridge? need to confirm with Angelica how it was split
2026-08-07 | LFBE02VI | 778 | 29280 | 0 | 0 | 37.635 | 11.29 | 26.345 | 11.29 | 1.3 | TWG-Wdbg | 26.89 | 2.3818 | 2.7281
2026-08-07 | JONR01CH | 605 | 22654 | 11629 | 11025 | 37.4446 | 19.2215 | 18.2231 | 19.2215 | 4 | LTW | 93.79 | 4.8794 | 3.866 | Kyle | left to pick: 1-23, 93, 95, 121, 123(1/2), 124-186
2026-08-07 | SLHM05PN | 691 | 15976 | 15976 | 0 | 23.1201 | 23.1201 | 0 | 23.1201 | 5.3 | LTW | 128.63 | 5.5636 | 0 | Mat | FC
2026-08-07 | MFLO01PG | 908 | 37921 | 37921 | 0 | 41.7632 | 41.7632 | 0 | 8.5782 | 3 | Gallo-J Winery | 48.39 | 5.641 | 0 | Uriel | FC
2026-08-08 | VKDD01CH | 726 | 18798 | 11890 | 6908 | 25.8926 | 16.3774 | 9.5152 | 16.3774 | 4 | LTW | 92.15 | 5.6267 | 2.3278 | Mat | Left to pick:95-73,71,68(1/2W),64-57,55,53(20 vines W)
2026-08-08 | JONR01CH | 605 | 22654 | 22654 | 0 | 37.4446 | 37.4446 | 0 | 18.2231 | 3 | LTW | 71.8 | 3.94 | 0 | Mat | FC
2026-08-08 | MJMJ02PG | 691 | 30586 | 30586 | 0 | 44.2634 | 44.2634 | 0 | 20.5586 | 5.3 | LTW | 121.5 | 5.9099 | 0 | Mat | FC
2026-08-09 | PRHZ01CH | 566 | 6935 | 6739 | 196 | 12.2527 | 11.9064 | 0.34629 | 11.9064 | 2.75 | LTW-Kosher | 64.73 | 5.4366 | 0.081854 | Luis | Left to picked: 100,105,108
2026-08-09 | PRHZ21CH | 691 | 6586 | 639 | 5947 | 9.5311 | 0.92475 | 8.6064 | 0.92475 | 0.25 | LTW-Kosher | 4.71 | 5.0933 | 1.9059 |  | Picked SW: 32-33,35-38,41-42
2026-08-10 | PRHZ15CB | 660 | 14817 | 4385 | 10432 | 22.45 | 6.6439 | 15.8061 | 6.6439 | 3 | LTW-Pine | 73.74 | 11.0988 | 7.6273 | Luis | 15-30,32,34, row 34 half picked
2026-08-10 | WHWH02PG | 691 | 23900 | 19743 | 4157 | 34.5876 | 28.5716 | 6.0159 | 28.5716 | 5 | Delicato | 113.6 | 3.976 | 1.04 | Mat | Left to pick: 6,8,10,12-25
2026-08-10 | DVDU05CH | 871 | 36095 | 11895 | 24200 | 41.4409 | 13.6567 | 27.7842 | 13.6567 | 4 | LTW | 89.01 | 6.5177 | 7.8734 | Uriel | Left to pick: 1-4,40,42-55,73-166
2026-08-10 | ONMI09CH | 807 | 30210 | 21495 | 8715 | 37.4349 | 26.6357 | 10.7993 | 26.6357 | 7 | Oneill | 165.56 | 6.2157 | 2.9185 | Leonardo | Left to pick: island plus 62(1/2),63-78, 79 (half) 80,82
2026-08-10 | VKDD01CH | 726 | 18798 | 18798 | 0 | 25.8926 | 25.8926 | 0 | 25.8926 | 2.6 | LTW | 59.94 | 2.315 | 0 | Mat | FC
2026-08-10 | DFDA07ND | 691 | 4595 | 4395 | 200 | 6.6498 | 6.3603 | 0.28944 | 6.3603 | 1 | LTW | 23.33 | 3.668 | 0.046159 | Luis | 34 and 35 left to pick
2026-08-10 | LFTO02SB | 622 | 34846 | 23990 | 10856 | 56.0225 | 38.5691 | 17.4534 | 38.5691 | 4 | ONeill | 95.12 | 2.4662 | 1.8715 | Kyle | 45(1/2), 46-49, 65(1/2), 91, 94-99, 102, 102-145
2026-08-10 | LFW105CH | 792 | 12945 | 0 | 0 | 16.3447 | 0 | 0 | 0 | 1 | LTW | 21.79 | 0 | 0 | Mat | FC
2026-08-10 | CLMO01BA | 681 | 22973 | 17422 | 5551 | 33.7342 | 25.583 | 8.1512 | 25.583 | 6 | LTW | 154.6 | 6.0431 | 2.1417 | Kelly | 1-20, 40,42,44,234-300,& 302.
2026-08-11 | WHWH02PG | 691 | 23900 | 23900 | 0 |  | 34.5876 | 0 | 6.0159 | 1.15 | Delicato | 25.8 | 4.2886 | 0 | Mat | FC
2026-08-11 | LF8004CH | 622 | 11433 | 11433 | 0 | 18.381 | 18.381 | 0 | 9.4019 | 2.25 | LTW | 54.98 | 5.8477 | 0 | Mat | FC
2026-08-11 | ONMI09CH | 807 | 30210 | 30210 | 0 | 37.4349 | 37.4349 | 0 | 10.7993 | 3 | Oneill | 66.04 | 6.1152 | 0 | Mat | FC
2026-08-11 | CLMO01BA | 681 | 22973 | 22973 | 0 | 33.7342 | 33.7342 | 0 | 8.1512 | 2 | LTW | 51.49 | 6.3168 | 0 | Uriel | FC
2026-08-11 | WHWH03AL | 691 | 20669 | 2343 | 18326 | 29.9117 | 3.3907 | 26.521 | 3.3907 | 0.58333 | LTW | 14.2 | 4.1879 | 4.829 | Mat | Picked: 82,83(1/3E),84,90-121.
2026-08-11 | LFTO02SB | 622 | 34846 | 34846 | 0 | 56.0225 | 56.0225 | 0 | 17.4534 | 2 | Oneill | 40.65 | 2.3291 | 0 | Mat | FC
2026-08-11 | PRHZ15CB | 660 | 14817 | 8608 | 6209 | 22.45 | 13.0424 | 9.4076 | 6.3985 | 3 | LTW-Pine & Kosher | 72.68 | 11.3589 | 4.6461 | Luis | Left to pick: 1-14,56-90 | Only 2 loads delivered for pine ridge - 1 kosher
2026-08-11 | MJMJ03CB | 726 | 14094 | 5055 | 9039 | 19.4132 | 6.9628 | 12.4504 | 6.9628 | 4 | LTW | 98.98 | 14.2155 | 7.6952 | Mat | Picked: 1-12,13(1/2W),14,16,18,20
2026-08-11 | PRHZ99SB | 660 | 1276 | 1276 | 0 | 1.9333 | 1.9333 | 0 | 1.9333 | 0.5625 | LTW-Kosher | 12.86 | 6.6517 | 0 | Luis | 2.25 gondolas - FC
2026-08-11 | CLPC02BA | 681 | 18907 | 11018 | 7889 | 27.7636 | 16.1791 | 11.5844 | 16.1791 | 3 | LTW | 74.11 | 4.5806 | 2.3071 | Uriel | Left to pick: 20,22-28,35-51,70-73,75 (50Vines) 78,80-103
2026-08-11 | PRHZ16CB | 660 | 4148 | 2379 | 1769 | 6.2848 | 3.6045 | 2.6803 | 3.6045 |  | LTW-Kosher | 23.15 | 6.4224 | 0.74844 | Rosendo | Left to pick: 50 south (special reserve) | TPA is not right - they didnt track tons per block
2026-08-11 | PRHZ17CB | 519 | 3672 | 1428 | 2244 | 7.0751 | 2.7514 | 4.3237 | 2.7514 |  | LTW-Kosher | 22.42 | 8.1484 | 1.5318 | Rosendo | Left to pick: 64,66,67,68,69,71,72,74, North of 74 | TPA is not right - they didnt track tons per block
2026-08-12 | LFRR08GB | 691 | 3193 | 3193 | 0 | 4.6208 | 4.6208 | 0 | 4.6208 | 1.85 | LTW | 41.29 | 8.9356 | 0 | Mat | FC
2026-08-12 | FFRY05CH | 622 | 15330 | 10423 | 4907 | 24.6463 | 16.7572 | 7.8891 | 16.7572 | 5 | Chateau St Jean | 110.39 | 6.5876 | 2.2596 | Mat | Left to pick: 14,16-44,52,54
2026-08-12 | PRHZ17CB | 519 | 3672 | 3672 | 0 | 7.0751 | 7.0751 | 0 |  |  | LTW-Kosher | 33 | 0 | 0 | Luis | FC
2026-08-12 | PRHZ99CB | 660 | 529 | 529 | 0 | 0.80152 | 0.80152 | 0 | 0.80152 |  | LTW-Kosher | 7.5 | 9.3573 | 0 | Luis | FC
2026-08-12 | PRHZ22CB | 519 | 2061 | 1125 | 936 | 3.9711 | 2.1676 | 1.8035 | 2.1676 |  | LTW-Kosher | 22.5 | 10.38 | 0.81391 | Luis | Left to pick: 20,16,14-9,7-1
2026-08-12 | MJMJ03CB | 726 | 14094 | 12294 | 1800 | 19.4132 | 16.9339 | 2.4793 | 9.9711 | 6 | LTW | 148.88 | 14.9312 | 1.6095 | Luis | Left to pick: 39,41.44-48 39 is half
2026-08-13 | PRHZ01CH | 566 | 6935 | 6935 | 0 | 12.2527 | 12.2527 | 0 | 0.34629 |  | LTW-Kosher | 1.5 | 4.3316 | 0 | Luis | FC
2026-08-13 | PRHZ21CH | 691 | 6586 | 5677 | 909 | 9.5311 | 8.2156 | 1.3155 | 7.2909 |  | LTW-Kosher | 42.58 | 5.8402 | 0.33403 | Luis | East left to pick 1-7,9,11,24-26, 11 half 25 has 14 26 has 18
2026-08-13 | MJMJ03CB | 726 | 14094 | 14094 | 0 | 19.4132 | 19.4132 | 0 | 2.4793 |  | LTW | 36 | 14.52 | 0 | Luis | FC - 6 gondolas
2026-08-13 | BAPE01CH | 726 | 30107 | 10354 | 19753 | 41.4697 | 14.2617 | 27.208 | 14.2617 | 4 | LTW | 94.16 | 6.6023 | 7.8102 | Mat | Picked: 20-48,50,53-60,62,79,80,82,84,110-130,132,139-160,161(1/2W),162,164
2026-08-13 | CL3A02SB | 622 | 30664 | 11226 | 19438 | 49.299 | 18.0482 | 31.2508 | 18.0482 | 6 | TWG-Wdbg | 142.66 | 7.9044 | 10.7399 | Mat | South island picked, East block picked: 182-135,133(1/2E),54,52-41,40(3/4W),38,36-1
2026-08-13 | MJMJ04CB | 726 | 26701 | 6023 | 20678 | 36.7782 | 8.2961 | 28.4821 | 8.2961 |  | LTW | 107.69 | 12.9807 | 16.0747 | Mat | South picked: 4-19 15.25 gondolas North picked: 1,2(1/2W),4,6. 2.75 gondola
2026-08-13 | PRHZ15CB | 660 | 14817 | 11356 | 3461 | 22.45 | 17.2061 | 5.2439 | 4.1636 | 2 | LTW-Kosher | 44.44 | 10.6734 | 2.4335 | Luis | Left to pick10,12-14,56-90, row 13 half picked
2026-08-14 | FFRY04CH | 566 | 8947 | 3135 | 5812 | 15.8074 | 5.5389 | 10.2686 | 5.5389 | 2 | Chateau St Jean | 40.82 | 7.3697 | 3.2903 | Leo | Left to pick: 1-55,56(3/4),57-61 (Leo count)
2026-08-14 | WHWH03AL | 691 | 20669 | 15188 | 5481 | 29.9117 | 21.9797 | 7.932 | 18.589 | 4 | Oneill | 93.27 | 5.0175 | 1.7304 | Abel | Left to pick: 29(30 vines),31,33-54,55(1/4),57 (Abel count)
2026-08-14 | PRHZ15CB | 660 | 14817 | 11845 | 2972 | 22.45 | 17.947 | 4.503 | 0.74091 |  | LTW-PINE | 9 | 12.1472 | 2.3782 | Luis | Left to pick: 12,14,56-67,69-90 | 1.5 gondolas
2026-08-14 | BEBU01ME | 807 | 37779 | 26564 | 11215 | 46.8141 | 32.917 | 13.8971 | 32.917 | 6 | Gallo-LIV | 141.68 | 4.3042 | 2.6007 | Mat | Picked: 3-13,15(3/4W),16,53(1/2E)55,57,59-66,75(1/2E),77,79-180
2026-08-14 | CL3A02SB | 622 | 30664 | 22202 | 8462 | 49.299 | 35.6945 | 13.6045 | 17.6463 | 6 | TWG-Wdbg | 144.32 | 8.1785 | 4.8376 | Mat | Picked all SW and SE islands, East block left to pick: 128(1/2W),126,124-97,95,93(1/2W),89-71,69(1/2E),68
2026-08-14 | PRHZ22CB | 519 | 2061 | 2061 | 0 | 3.9711 | 3.9711 | 0 | 1.8035 |  | LTW-PINE | 22.5 | 12.476 | 0 | Luis | FC | 2.75 gondolas
2026-08-14 | PRHZ11CB | 660 | 14099 | 4447 | 9652 | 21.3621 | 6.7379 | 14.6242 | 6.7379 |  | LTW-PINE | 96 | 14.2478 | 9.0593 | Luis | Picked: 1,3,27,29,31-50,79,82, Row 27 has 20 unpicked vines | 16 gondolas
2026-08-14 | PRHZ14CB | 660 | 1954 | 1954 | 0 | 2.9606 | 2.9606 | 0 | 2.9606 |  | LTW-PINE | 22.5 | 7.5998 | 0
2026-08-15 | FFRY04CH | 566 | 8947 | 8545 | 402 | 15.8074 | 15.0972 | 0.71025 | 9.5583 | 3 | Chateau St Jean | 72 | 7.5327 | 0.23261 | Mat | Left to pick: 16,19,21(1/4),22,25 - Leaving in field DFC
2026-08-15 | DVDU05CH | 871 | 36095 | 36095 | 0 | 41.4409 | 41.4409 | 0 | 27.7842 | 8 | LTW | 183.42 | 6.6016 | 0 | Uriel | FC
2026-08-15 | BEBU01ME | 807 | 37779 | 37779 | 0 | 46.8141 | 46.8141 | 0 | 13.8971 | 2 | Gallo | 36.78 | 2.6466 | 0 | Mat | FC
2026-08-15 | LFRT03AN | 691 | 195 | 195 | 0 | 0.2822 | 0.2822 | 0 | 0.2822 |  | LTW | 1.35 | 4.7838 | 0 | Mat | FC
2026-08-18 | FFRY01PN | 622 | 4778 | 4778 | 0 | 7.6817 | 7.6817 | 0 | 7.6817 |  |  | 57 | 7.4203 | 0 |  | Trial section - FC
2026-08-19 | FFRY01PN | 622 | 18541 | 6667 | 11874 | 29.8087 | 10.7186 | 19.09 | 10.7186 |  |  | 87 | 8.1167 | 6.7369 |  | Regular - Left to pick: 16,18-37,61-95,97,99 | Teams message shows 18-32 - should be 18-37
2026-08-20 | WHWH03AL | 691 | 20669 | 20669 | 0 | 29.9117 | 29.9117 | 0 | 7.932 | 1.7 | Oneill | 37.79 | 4.7643 | 0 | Mat | FC
2026-08-17 | CL3A02SB | 622 | 30664 | 30664 | 0 | 49.299 | 49.299 | 0 | 13.6045 | 4.75 | TWG-Wdbg | 113.17 | 8.3186 | 0 | Mat | FC
2026-08-17 | PRHZ15CB | 660 | 14817 | 14817 | 0 | 22.45 | 22.45 | 0 | 4.503 |  | LTW-PINE | 46.5 | 10.3264 | 0 | Luis | FC - 7.75 gondolas. Assuming remainder of 6 loads from prince came from B11
2026-08-17 | MJMJ04CB | 726 | 26701 | 14172 | 12529 | 36.7782 | 19.5207 | 17.2576 | 11.2245 | 6 | LTW-PINE | 154.36 | 13.752 | 10.3186 | Luis | Left to pick: 27,29-81,84-85, row 30 is 3/4 picked
2026-08-17 | 98OK07ME | 691 | 25345 | 8336 | 17009 | 36.6787 | 12.0637 | 24.6151 | 12.0637 | 3 | LTW | 75.94 | 6.2949 | 6.737 | Uriel | Left to pick: 1-80
2026-08-17 | PRHZ11CB | 660 | 14099 | 9283 | 4816 | 21.3621 | 14.0652 | 7.297 | 7.3273 |  | LTW-PINE | 97.5 | 13.3065 | 4.2216 | Luis | Left to pick: 18,20,22-28,30,50,55,57,59-73,76, ROWS 20 AND 50 HALF PICKED - tonnage is 6 loads minus 7.75 gondolas from B15
2026-08-18 | FFRY01PN | 622 | 23319 | 23114 | 205 | 37.4904 | 37.1608 | 0.32958 | #REF! | 6 | Prevail | 144 | 0 | 0 | Mat | Left to pick: 78
2026-08-18 | ONMI07+08 | 807 | 61566 | 36258 | 25308 | 76.29 | 44.9294 | 31.3606 | 44.9294 | 11 | ONeill | 255.84 | 5.6943 | 7.7642
2026-08-18 | ONMI08ME | 807 | 30658 | 20037 | 10621 | 37.9901 | 24.829 | 13.1611 | 24.829 |  | Oneill | 0 | 0 | 0 |  | Left to pick: 4, 6, 8-29, 33, 35-45, 47, 49(1/2E,) 80-82, 84(1/2W)
2026-08-18 | ONMI07ME | 807 | 30908 | 16221 | 14687 | 38.2999 | 20.1004 | 18.1995 | 20.1004 |  | Oneill | 0 | 0 | 0 |  | Left to pick. 1-3, 4(1/2W,) 5, 7, 40-77, 110, 112-132
2026-08-18 | MJMJ04CB | 726 | 26701 | 21782 | 4919 | 36.7782 | 30.0028 | 6.7755 | 10.4821 | 6 | LTW-Pine | 148.77 | 14.1928 | 4.181 | Luis | Left to pick 45,47,49,51-62,64,72-78,Row 61 has 30 unpicked vines
2026-08-18 | PRHZ11CB | 660 | 14099 | 14099 | 0 | 21.3621 | 21.3621 | 0 | 7.297 | 4.25 | LTW-Pine | 107.28 | 14.702 | 0 | Luis | FC
2026-08-18 | PPBR03CH | 622 | 25496 | 11511 | 13985 | 40.9904 | 18.5064 | 22.4839 | 18.5064 | 8 | TWG-Wdbg | 200.33 | 10.8249 | 10.582 |  | some from craig?
2026-08-18 | PPBR03CH-E | 622 | 12034 | 0 | 12034 | 19.3473 | 0 | 19.3473 | 0 |  |  | 0 | 0 | 0 |  | Left: all
2026-08-18 | PPBR03CH-MID | 622 | 8666 | 7254 | 1412 | 13.9325 | 11.6624 | 2.2701 | 11.6624 |  |  | 0 | 0 | 0 |  | Left: 13,16,31,32,35-38
2026-08-18 | PPBR03CH-W | 622 | 4796 | 4257 | 539 | 7.7106 | 6.8441 | 0.86656 | 6.8441 |  |  |  | 0 | 0 |  | Left 13,16,31,32,36,36
2026-08-18 | PPCR02CH | 681 | 22329 | 3346 | 18983 | 32.7885 | 4.9134 | 27.8752 | 4.9134 |  | TWG-Wdbg | 15 | 3.0529 | 3.7 |  | Picked: 55,48,61,65,92,94-103,105,179 | 2.5 gondolas
2026-08-18 | PRHZ16CB | 660 | 4148 | 2501 | 1647 | 6.2848 | 3.7894 | 2.4955 |  | 0.25 | LTW-Pine | 4.41 | 0 | 0 | Luis | Left to pick 50-32,29-22 | 0.25 gondola or 0.25 load?
2026-08-19 | FFRY05CH | 622 | 15330 | 14763 | 567 | 24.6463 | 23.7347 | 0.91158 | 6.9775 | 2 | Vinwood | 48 | 6.8793 | 0.27265 | Mat | Left to pick:18(1/4),21,28,29,32(1/2) about 1 gondola
2026-08-19 | ONMI07ME | 807 | 30908 | 30908 | 0 | 38.2999 | 38.2999 | 0 | 18.1995 |  | Oneill | 0 | 0 | 0 | Mat | FC 7.25 total loads
2026-08-19 | ONMI08ME | 807 | 30658 | 30658 | 0 | 37.9901 | 37.9901 | 0 | 13.1611 |  | Oneill | 0 | 0 | 0 | Mat | FC 7.25 total loads
2026-08-19 | PPBR03CH | 622 | 25496 | 21657 | 3839 | 40.9904 | 34.8183 | 6.172 | 16.3119 | 7 | TWG-Wdbg | 142.78 | 8.7531 | 2.3489 |  | some from craig?
2026-08-19 | PPBR03CH-E | 622 | 12034 | 8195 | 3839 | 19.3473 | 13.1752 | 6.172 | 13.1752 |  |  | 0 | 0 | 0 | uriel | left to pick east block 49,51-59,61,63,65,69-70,89,91-108
2026-08-19 | PPBR03CH-MID | 622 | 8666 | 8666 | 0 | 13.9325 | 13.9325 | 0 | 2.2701 |  |  | 0 | 0 | 0 | uriel
2026-08-19 | PPBR03CH-W | 622 | 4796 | 4796 | 0 | 7.7106 | 7.7106 | 0 | 0.86656 |  |  | 0 | 0 | 0 | uriel
2026-08-19 | PPCR02CH | 681 | 22329 | 12478 | 9851 | 32.7885 | 18.3231 | 14.4655 | 13.4097 |  | TWG-Wdbg | 33 | 2.4609 | 1.5477 | uriel | 1-48,50-52,54-57,110,112,114-147 5.5 Gondola
2026-08-19 | CLMN01SY | 622 | 36996 | 20828 | 16168 | 59.4791 | 33.4855 | 25.9936 | 33.4855 | 4 | Stonewall | 96 | 2.8669 | 3.2401 | Uriel
2026-08-19 | CLMN01SY-E | 622 | 21239 | 15232 | 6007 | 34.1463 | 24.4887 | 9.6576 | 24.4887 |  |  | 0 | 0 | 0 |  | East left 1-33,35,62-67,69,71,84-87,89,114,116,155-175
2026-08-19 | CLMN01SY-W | 622 | 15757 | 5596 | 10161 | 25.3328 | 8.9968 | 16.336 | 8.9968 |  |  | 0 | 0 | 0 |  | West left 1-52,54,56,99,101-113 EXT 73-112
2026-08-20 | ZLSO01PN | 622 | 50920 | 13253 | 37667 | 81.865 | 21.3071 | 60.5579 | 21.3071 | 6 | Gallo-LIV | 148.41 | 6.9653 | 18.3393 | Luis | picked 47,49,50,106-134,136,159,161,163-200,249,255-256, row 136 and 162 half picked
2026-08-20 | PPBR03CH | 622 | 25496 | 25496 | 0 | 40.9904 | 40.9904 | 0 | 6.172 |  | TWG | 57.5 | 9.3162 | 0 | Uriel | FC
2026-08-20 | PPCR02CH | 681 | 22329 | 22329 | 0 | 32.7885 | 32.7885 | 0 | 14.4655 |  | TWG | 45.3 | 3.1316 | 0 | Uriel | FC
2026-08-20 | DFDA04ZN | 691 | 5487 | 5487 | 0 | 7.9407 | 7.9407 | 0 | 7.9407 | 2 | Delicato | 48 | 6.0448 | 0 | Mat | FC
2026-08-20 | LFEX02SY | 605 | 11744 | 11744 | 0 | 19.4116 | 19.4116 | 0 | 19.4116 | 4 | Bronco | 83.74 | 4.3139 | 0 |  | FC
2026-08-20 | CLMN01SY | 622 | 36996 | 36996 | 0 | 59.4791 | 59.4791 | 0 | 25.9936 | 3 | Bronco | 72 | 2.7699 | 0 |  | FC
2026-08-20 | CLLA01ME | 681 | 49099 | 0 | 0 | 72.0984 | 0 | 0 | 0 |  | DELTA PACKING | 0 | 0 | 0
2026-08-20 | LFEX01SA | 605 | 10120 | 0 | 0 | 16.7273 | 0 | 0 | 0 |  | DELTA PACKING | 0 | 0 | 0
2026-08-20 | CLBC00VD | 681 | 4658 | 0 | 0 | 6.8399 | 0 | 0 | 0 |  | DELTA PACKING | 0 | 0 | 0
2026-08-21 | ZLSO01PN | 622 | 51248 | 32819 | 18429 | 82.3923 | 52.7637 | 29.6286 | 30.9293 | 10 | Gallo-LIV | 235 | 7.598 | 9.7877 | Luis | Left to pick 1-12,14,16-29,53,57-84,87,89,91-103,135-142,144,219,221,223-225,237,239-246,248,250,252,283-301 Row 11 is halfway picked Row 219 has 20 unpicked vines Row 240 has 15 unpicked vines Row 252 has 15 unpicked vines Row 136 is halfway picked
2026-08-21 | BAPE01CH | 726 | 30107 | 30107 | 0 | 41.4697 | 41.4697 | 0 | 27.208 | 7.75 | LTW | 179.11 | 6.583 | 0 | Mat | FC
2026-08-21 | CLLA01ME | 681 | 49099 |  | 0 | 72.0984 | 0 | 0 | 0 |  | DELTA PACKING | 0 | 0
2026-08-21 | LFEX01SA | 605 | 10120 |  | 0 | 16.7273 | 0 | 0 | 0 |  | DELTA PACKING | 0 | 0
2026-08-23 | CLR202CH | 681 | 47208 | 8417 | 38791 | 69.3216 | 12.3598 | 56.9618 | 12.3598 | 3 | LTW | 72 | 5.8254 | 14.4271 | Mat | Picked: 79-88,90,92,106-117,119,121,123
2026-08-23 | CLBC02CH | 681 | 40584 | 10521 | 30063 | 59.5947 | 15.4493 | 44.1454 | 15.4493 | 3 | LTW | 68.18 | 4.4131 | 8.4704 | Mat | Picked: 221-227,232,246-257,259,261,272-281,283
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0

## Sheet1 (hidden)
Code | Variety | Block | Acres Remaining | Est. Tons Remaining | Last Brix Reading
CLAT05CS | CS | Clements Atkins B5 CS | 34.92 | 244.44 | 23.5 on 10/20
DBAI04CS | CS | Donald Airport B4 CS | 9.27 | 64.89 | 24.3 on 10/20
LAPR05CS | CS | La Prima B5 CS | 43.1 | 275 | 23.1 on 10/20
MRPR01CS | CS | MRP B1 CS | 35.04 | 262.8 | 23.1 on 10/20
POCR03CS | CS | Craig Patriot Oaks - Hillltop B3 CS | 59.66 | 447.45 | 24.4 on 10/20

## Stats (hidden)
| Sum of ACRES PICKED SINCE LAST COUNT | Sum of TONS PICKED TODAY
2025-08-07 | 21.975 | 116.02
2025-08-08 | 19.6543 | 106.16
2025-08-11 | 6.1266 | 40
2025-08-12 | 33.744 | 270.08
2025-08-13 | 26.1789 | 277.99
2025-08-14 | 55.4777 | 480.66
2025-08-15 | 40.76 | 394.51
2025-08-18 | 71.2771 | 546.99
2025-08-19 | 61.4743 | 500.599
2025-08-20 | 82.2723 | 630.08
2025-08-21 | 89.2035 | 593.8
2025-08-22 | 33.7007 | 221.03
2025-08-23 | 7.58 | 93.72
2025-08-25 | 81.2403 | 616.57
2025-08-26 | 118.7024 | 848.72
2025-08-27 | 83.2159 | 621.66
2025-08-28 | 85.0998 | 600.57
2025-08-29 | 91.3432 | 583.28
2025-08-30 | 44.9859 | 404.63
2025-08-31 | 38.3787 | 227.48
2025-09-01 | 80.628 | 626.145
2025-09-02 | 93.3186 | 627.85
2025-09-03 | 130.7454 | 973.9
2025-09-04 | 90.9978 | 768.05
2025-09-05 | 115.0617 | 1071.91
2025-09-06 | 96.0495 | 907.12
2025-09-07 | 62.4613 | 563.71
2025-09-08 | 127.8203 | 894.13
2025-09-09 | 90.332 | 865.97

## Source List (hidden)
Prince CB |  |  |  |  | VINEYARD CODE | SUB-BLOCK | REGION | SPACING | TOTAL VINES | ROW COUNT ACRES | NOTES | Updated: | 2024-07-30 | 12:00
BLK | AC. | TPA | EST TONS |  | 98OK01CS | 98OK01CS | CLEMENTS | 726 | 16379 | 22.5606 |  | By: | Maria Z.
5 | 0.37 | 2.64 | 0.9768 |  | 98OK02CS | 98OK02CS | CLEMENTS | 726 | 11178 | 15.3967
6 | 3.15 | 5.82 | 18.333 |  | 98OK03MA | 98OK03MA | CLEMENTS | 691 | 13027 | 18.8524
[5 empty] | 98OK04CS | 98OK04CS | CLEMENTS | 691 | 18124 | 26.2287
10 | 4.25 | 2.73 | 11.6025 |  | 98OK05CS | 98OK05CS | CLEMENTS | 691 | 13746 | 19.8929
[5 empty] | 98OK06CS | 98OK06CS | CLEMENTS | 691 | 15567 | 22.5282
14 | 3.03 | ? | 24.24 | estimated 8tpa | 98OK07ME | 98OK07ME | CLEMENTS | 691 | 25345 | 36.6787
[5 empty] | 98OK08PS | 98OK08PS | CLEMENTS | 691 | 16485 | 23.8567
[5 empty] | 98OK09CS | 98OK09CS | CLEMENTS | 726 | 27935 | 38.478
[5 empty] | 98OK10ZN | 98OK10ZN | CLEMENTS | 691 | 12621 | 18.2648
[5 empty] | 98OK11CF | 98OK11CF | CLEMENTS | 807 | 16549 | 20.5068
[5 empty] | ARDA01CS | ARDA01CS | LODI | 622 | 22639 | 36.3971
[5 empty] | BAPE01CH | BAPE01CH | LODI | 726 | 30107 | 41.4697
[5 empty] | BAVC01ZN | BAVC01ZN | CLEMENTS | 622 | 10298 | 16.5563
[5 empty] | BAVC02PR | BAVC02PR | CLEMENTS | 622 | 7170 | 11.5273
[5 empty] | BEBU01ME | BEBU01ME | LODI | 807 | 37779 | 46.8141
[5 empty] | BHCH01CS | BHCH01CS-1 | CLEMENTS | 622 | 2814 | 4.5241
[5 empty] | BHCH01CS | BHCH01CS-2 | CLEMENTS | 622 | 2398 | 3.8553
[5 empty] | BHCH01CS | BHCH01CS-3 | CLEMENTS | 622 | 751 | 1.2074
[5 empty] | BHCH01CS | BHCH01CS-4 | CLEMENTS | 622 | 2031 | 3.2653
15 | 13.09 | 11.52 | 150.7968 |  | BHCH01CS | BHCH01CS-5 | CLEMENTS | 622 | 1215 | 1.9534
16 | 0 | 8.5 | 0 |  | BHCH01CS | BHCH01CS-6 | CLEMENTS | 622 | 612 | 0.98392
17 | 0 | 11.11 | 0 |  | BHCH01CS | BHCH01CS-7 | CLEMENTS | 622 | 2600 | 4.1801
|  |  | 205.9491 |  | BHCH01CS | BHCH01CS-8 | CLEMENTS | 622 | 1618 | 2.6013
[5 empty] | BHCH01CS | BHCH01CS-9 | CLEMENTS | 622 | 1283 | 2.0627
[5 empty] | BHCH01CS | BHCH01CS-10 | CLEMENTS | 622 | 1455 | 2.3392
[5 empty] | BHCH01CS | BHCH01CS-11 | CLEMENTS | 622 | 774 | 1.2444
[5 empty] | BHCH01CS | BHCH01CS-12 | CLEMENTS | 622 | 3922 | 6.3055
[5 empty] | BHCH01CS | BHCH01CS-13 | CLEMENTS | 622 | 5743 | 9.2331
[5 empty] | BHCH01CS | BHCH01CS-ALL | CLEMENTS | 622 | 27216 | 43.7556
[5 empty] | BSHMOHCS | BSHMOHCS | CLEMENTS | 605 | 2554 | 4.2215
BHCH01CS |  |  |  |  | CL3A01PV | CL3A01PV | CLEMENTS | 681 | 60308 | 88.558
set | vines |  |  |  | CL3A02SB | CL3A02SB | CLEMENTS | 622 | 30664 | 49.299
7 | 2600 |  |  |  | CL3A04PV | CL3A04PV | CLEMENTS | 681 | 36152 | 53.0866
2 | 2398 | all |  |  | CL3A05ZN | CL3A05ZN | CLEMENTS | 681 | 28396 | 41.6975
6 | 612 | fc |  |  | CLAT01CS | CLAT01CS | CLEMENTS | 681 | 26721 | 39.2379
6 | 612 | fc |  |  | CLAT01CS | CLAT01CS-DISCH | CLEMENTS | 681 | 23968 | 35.1953
[5 empty] | CLAT01CS | CLAT01CS-NS | CLEMENTS | 681 | 2753 | 4.0426
[5 empty] | CLAT02CH | CLATCH-84ac | CLEMENTS | 681 | 57068 | 83.8003
8 | 1618 | fc |  |  | CLAT02CH | CLAT02CH | CLEMENTS | 681 | 55701 | 81.793
5 | 1215 |  |  |  | CLAT05CS | CLAT05CS | CLEMENTS | 681 | 23399 | 34.3598
5 | 1215 |  |  |  | CLAT05CS | CLAT05CS-N | CLEMENTS | 681 | 3830 | 5.6241
5 | 1215 |  |  |  | CLAT05CS | CLAT05CS-S | CLEMENTS | 681 | 19569 | 28.7357
11 | 774 |  |  |  | CLBC00VD | CLBC00VD | CLEMENTS | 681 | 4658 | 6.8399
1 | 2814 | fc |  |  | CLBC01PG | CLBC01PG | CLEMENTS | 681 | 26421 | 38.7974
4 | 2031 | fc |  |  | CLBC02CH | CLBC02CH | CLEMENTS | 681 | 40584 | 59.5947 | 2022 Harvest Status shows 40388?
[5 empty] | CLLA01ME | CLLA01ME | CLEMENTS | 681 | 49099 | 72.0984
12 | 3922 | fc |  |  | CLLA01ME | CLLA01ME-N | CLEMENTS | 681 | 43557 | 63.9604
[5 empty] | CLLA01ME | CLLA01ME-S | CLEMENTS | 681 | 5542 | 8.138
[5 empty] | CLMN01SY | CLMN01SY | CLEMENTS | 622 | 36996 | 59.4791
13 | 5743 |  |  |  | CLMN01SY | CLMN01SY-E | CLEMENTS | 622 | 21239 | 34.1463
13 | 5743 |  |  |  | CLMN01SY | CLMN01SY-W | CLEMENTS | 622 | 15757 | 25.3328
| 26769 |  |  |  | CLMN02PV | CLMN02PV | CLEMENTS | 622 | 9103 | 14.635
[5 empty] | CLMNOHPS | CLMNOHPS | CLEMENTS | 622 | 20354 | 32.7235
[5 empty] | CLMN03PS | CLMN03PS | CLEMENTS | 622 | 3004 | 4.8296
[5 empty] | CLMN04PS | CLMN04PS | CLEMENTS | 622 | 7450 | 11.9775
[5 empty] | CLMN05PS | CLMN05PS | CLEMENTS | 622 | 9900 | 15.9164
[5 empty] | CLMO01BA | CLMO01BA | CLEMENTS | 681 | 22973 | 33.7342
[5 empty] | CLNR01CS | CLNR01CS | CLEMENTS | 726 | 43036 | 59.2782
[5 empty] | CLOK01ME | CLOK01ME | CLEMENTS | 681 | 68165 | 100.0954
[5 empty] | CLOK02CS | CLOK02CS | CLEMENTS | 681 | 70478 | 103.4919
[5 empty] | CLOK02CS | CLOK02CS-MAIN | CLEMENTS | 681 | 62991 | 92.4978
[5 empty] | CLOK02CS | CLOK02CS-SW | CLEMENTS | 681 | 7487 | 10.9941
[5 empty] | CLPC01ME | CLPC01ME | CLEMENTS | 681 | 25777 | 37.8517
[5 empty] | CLPC01ME | CLPC01ME-K | CLEMENTS | 681 | 17266 | 25.3539
[5 empty] | CLPC01ME | CLPC01ME-NS | CLEMENTS | 681 | 8511 | 12.4978
[5 empty] | CLPC02BA | CLPC02BA | CLEMENTS | 681 | 18907 | 27.7636
[5 empty] | CLPC03ME | CLPC03ME | CLEMENTS | 681 | 29269 | 42.9794
[5 empty] | CLPC06PR | CLPC06PR | CLEMENTS | 681 | 54128 | 79.4831
[5 empty] | CLPC07CS | CLPC07CS | CLEMENTS | 681 | 51444 | 75.5419
[5 empty] | CLPC4APR | CLPC4APR | CLEMENTS | 807 | 46215 | 57.2677
[5 empty] | CLPC4BCH | CLPC4BCH | CLEMENTS | 726 | 43649 | 60.1226
[5 empty] | CLPT01CS | CLPT01CS | CLEMENTS | 681 | 56217 | 82.5507
[5 empty] | CLR101ME | CLR101ME | CLEMENTS | 681 | 45056 | 66.1615
[5 empty] | CLR101ME | CLR101ME-E | CLEMENTS | 681 | 24644 | 36.188
[5 empty] | CLR101ME | CLR101ME-W | CLEMENTS | 681 | 20412 | 29.9736
[5 empty] | CLR201MA | CLR201MA | CLEMENTS | 681 | 22011 | 32.3216
[5 empty] | CLR202CH | CLR202CH | CLEMENTS | 681 | 47208 | 69.3216
[5 empty] | CO8802CH | CO8802CH | CLEMENTS | 622 | 19702 | 31.6752
[5 empty] | DBAI02SA | DBAI02SA | LODI | 778 | 7703 | 9.901
[5 empty] | DBAI03ZN | DBAI03ZN | LODI | 622 | 5633 | 9.0563
[5 empty] | DBAI04CS | DBAI04CS | LODI | 622 | 5670 | 9.1158
[5 empty] | DBDA05CH | DBDA05CH | LODI | 622 | 6057 | 9.7379
[5 empty] | DFDA01CS | DFDA01CS | LODI | 622 | 9349 | 15.0305
[5 empty] | DFDA04ZN | DFDA04ZN | LODI | 691 | 5487 | 7.9407
[5 empty] | DFDA07ND | DFDA07ND | LODI | 691 | 4595 | 6.6498
[5 empty] | DULA01CS | DULA01CS | CLEMENTS | 622 | 2281 | 3.6672
[5 empty] | DVDU02SB | DVDU02SB | DELTA | 726 | 28200 | 38.843
[5 empty] | DVDU03SB | DVDU03SB | DELTA | 605 | 28346 | 46.8529
[5 empty] | DVDU04SB | DVDU04SB | DELTA | 605 | 20210 | 33.405
[5 empty] | DVDU06VI | DVDU06VI | DELTA | 545 | 2755 | 5.055
[5 empty] | DVDU07MC | DVDU07MC | DELTA | 545 | 15354 | 28.1725
[5 empty] | DVDU08PN | DVDU08PN | DELTA | 622 | 28345 | 45.5707
[5 empty] | DVDU1CSB | DVDU1CSB | DELTA | 726 | 32514 | 44.7851
[5 empty] | DVMA01PN | DVMA01PN | DELTA | 691 | 30586 | 44.2634
[5 empty] | DVMA01PN | DVMA01PN-EAST | DELTA | 691 | 7826 | 11.3256
[5 empty] | DVMA01PN | DVMA01PN-WEST | DELTA | 691 | 22760 | 32.9378
[5 empty] | DVMA02PG | DVMA02PG | DELTA | 908 | 94178 | 103.7203
[5 empty] | FDJA01TO | FDJA01TO | LODI | 681 | 13593 | 19.9604
[5 empty] | FDJA02TE | FDJA02TE | LODI | 681 | 13612 | 19.9883
[5 empty] | FDJA03MA | FDJA03MA | LODI | 681 | 24401 | 35.8311
[5 empty] | FDJA04ME | FDJA04ME | LODI | 681 | 29289 | 43.0088
[5 empty] | FDJA05ME | FDJA05ME | LODI | 778 | 14077 | 18.0938
[5 empty] | FDJA06TA | FDJA06TA | LODI | 681 | 5471 | 8.0338
[5 empty] | FFRY01PN | FFRY01PN | DELTA | 622 | 23319 | 37.4904
[5 empty] | FFRY02PN | FFRY02PN | DELTA | 622 | 9294 | 14.9421
[5 empty] | FFRY04CH | FFRY04CH | DELTA | 566 | 8947 | 15.8074
[5 empty] | FFRY05CH | FFRY05CH | DELTA | 622 | 15330 | 24.6463
[5 empty] | FFRY09PN | FFRY09PN | DELTA | 622 | 2749 | 4.4196
[5 empty] | FFRY10PN | FFRY10PN | DELTA | 622 | 5853 | 9.41
[5 empty] | FFRY15CB | FFRY15CB | DELTA | 558 | 22433 | 40.2025
[5 empty] | FFRY3BAL | FFRY3BAL | DELTA | 807 | 15190 | 18.8228
[5 empty] | FFRY99PN | FFRY99PN | DELTA | 660 | 11709 | 17.7409
[5 empty] | GEWENOCH | GEWENOCH | CLEMENTS | 622 | 15945 | 25.635
[5 empty] | GZWESOCH | GZWESOCH | CLEMENTS | 622 | 16618 | 26.717
[5 empty] | HEBO01CS | HEBO01CS | CLEMENTS | 622 | 10509 | 16.8955
[5 empty] | HIHV04CS | HIHV04CS | LODI | 691 | 30602 | 44.2865
[5 empty] | HIHV05PS | HIHV05PS | LODI | 691 | 39054 | 56.5181
[5 empty] | IWHM01CS | IWHM01CS | LODI | 622 | 2378 | 3.8232
[5 empty] | JONR01CH | JONR01CH | LODI | 605 | 22654 | 37.4446
[5 empty] | JONR02SB | JONR02SB | LODI | 726 | 4941 | 6.8058
[5 empty] | JONR03GV | JONR03GV | LODI | 726 | 3247 | 4.4725
[5 empty] | KBBR01ZN | KBBR01ZN | CLEMENTS | 622 | 17569 | 28.246
[5 empty] | KBBR02TD | KBBR02TD | CLEMENTS | 691 | 15293 | 22.1317
[5 empty] | LAPR02CH | LAPR02CH | LODI | 691 | 23449 | 33.9349
[5 empty] | LAPR03ME | LAPR03ME | LODI | 691 | 23354 | 33.7974
[5 empty] | LAPR04PS | LAPR04PS | LODI | 778 | 33795 | 43.4383
[5 empty] | LAPR05CS | LAPR05CS | LODI | 778 | 33260 | 42.7506
[5 empty] | LF1001CS | LF1001CS | LODI | 622 | 30330 | 48.7621
[5 empty] | LF1002PS | LF1002PS | LODI | 807 | 39630 | 49.1078
[5 empty] | LF3801CS | LF3801CS | LODI | 622 | 29134 | 46.8392
[5 empty] | LF3801CS | LF3801CS-sprawl | LODI | 622 | 11789 | 18.9534
[5 empty] | LF3801CS | LF3801CS-vsp | LODI | 622 | 17345 | 27.8859
[5 empty] | LF8001TD | LF8001TD | LODI | 622 | 15349 | 24.6768
[5 empty] | LF8002PV | LF8002PV | LODI | 622 | 16062 | 25.8232
[5 empty] | LF8003PS | LF8003PS | LODI | 622 | 4428 | 7.119
[5 empty] | LF8004CH | LF8004CH | LODI | 622 | 11433 | 18.381
[5 empty] | LFBE01CS | LFBE01CS | LODI | 726 | 41905 | 57.7204
[5 empty] | LFBE02VI | LFBE02VI | LODI | 778 | 29280 | 37.635
[5 empty] | LFBT01CH | LFBT01CH | LODI | 807 | 30338 | 37.5936
[5 empty] | LFBT02SB | LFBT02SB | LODI | 726 | 27203 | 37.4697
[5 empty] | LFDA02PG | LFDA02PG | LODI | 908 | 8809 | 9.7015
[5 empty] | LFDA03CH | LFDA03CH | LODI | 622 | 11341 | 18.2331
[5 empty] | LFEX01SA | LFEX01SA | LODI | 605 | 10120 | 16.7273
[5 empty] | LFEX02SY | LFEX02SY | LODI | 605 | 11744 | 19.4116
[5 empty] | LFEX03VI | LFEX03VI | LODI | 605 | 9777 | 16.1603
[5 empty] | LFEX04VI | LFEX04VI | LODI | 778 | 9125 | 11.7288
[5 empty] | LFGC01CS | LFGC01CS | LODI | 726 | 59411 | 81.8333
[5 empty] | LFGC01CS | LFGC01CS-N | LODI | 726 | 45642 | 62.8678
[5 empty] | LFGC01CS | LFGC01CS-S | LODI | 726 | 13769 | 18.9656
[5 empty] | LFRA01CS | LFRA01CS | LODI | 681 | 23633 | 34.7034
[5 empty] | LFRA02CF | LFRA02CF | LODI | 726 | 10726 | 14.7741
[5 empty] | LFRR01PV | LFRR01PV | LODI | 908 | 5593 | 6.1597
[5 empty] | LFRR02CS | LFRR02CS | LODI | 726 | 8094 | 11.1488
[5 empty] | LFRR03CS | LFRR03CS | LODI | 807 | 23285 | 28.8538
[5 empty] | LFRR04CS | LFRR04CS | LODI | 622 | 5198 | 8.3569
[5 empty] | LFRR05MP | LFRR05MP | LODI | 691 | 3134 | 4.5355
[5 empty] | LFRR06AG | LFRR06AG | LODI | 807 | 5324 | 6.5973
[5 empty] | LFRR07PB | LFRR07PB | LODI | 691 | 3444 | 4.9841
[5 empty] | LFRR08GB | LFRR08GB | LODI | 691 | 3193 | 4.6208
[5 empty] | LFRT01ND | LFRT01ND | LODI | 691 | 2220 | 3.2127
[5 empty] | LFRT02PR | LFRT02PR | LODI | 691 | 18780 | 27.178
[5 empty] | LFRT03AN | LFRT03AN | LODI | 691 | 195 | 0.2822
[5 empty] | LFTO01CS | LFTO01CS | LODI | 726 | 41547 | 57.2273
[5 empty] | LFTO02SB | LFTO02SB | LODI | 622 | 34846 | 56.0225
[5 empty] | LFW104CS | LFW104CS | LODI | 726 | 39384 | 54.2479
[5 empty] | LFW202TD | LFW202TD | LODI | 605 | 19356 | 31.9934
[5 empty] | LFW301CS | LFW301CS | LODI | 681 | 27160 | 39.8825
[5 empty] | LFW302SB | LFW302SB | LODI | 622 | 30523 | 49.0723
[5 empty] | MEJA03CS | MEJA03CS | LODI | 726 | 22202 | 30.5813
[5 empty] | MFLO01PG | MFLO01PG | CLEMENTS | 908 | 37921 | 41.7632
[5 empty] | MFLO02TE | MFLO02TE | CLEMENTS | 778 | 17071 | 21.9422
[5 empty] | MFRN01PN | MFRN01PN | DELTA | 807 | 27381 | 33.9294
[5 empty] | MFRN02PN | MFRN02PN | DELTA | 807 | 36610 | 45.3656
[5 empty] | MFRN03PG | MFRN03PG | DELTA | 807 | 36108 | 44.7435
[5 empty] | MJMJ01CH | MJMJ01CH | DELTA | 622 | 17694 | 28.4469
[5 empty] | MJMJ02PG | MJMJ02PG-old | DELTA | 691 | 30372 | 43.9537
[5 empty] | MJMJ02PG | MJMJ02PG-retrain | DELTA | 691 | 15223 | 22.0304
[5 empty] | MJMJ03CB | MJMJ03CB | DELTA | 726 | 14094 | 19.4132
[5 empty] | MJMJ04CB | MJMJ04CB | DELTA | 726 | 26701 | 36.7782
[5 empty] | MKJA04CS | MKJA04CS | LODI | 726 | 25885 | 35.6543
[5 empty] | MRPR01CS | MRPR01CS | CLEMENTS | 605 | 20970 | 34.6612
[5 empty] | MUMU01SB | MUMU01SB | LODI | 605 | 12811 | 21.1752
[5 empty] | MUMU02PG | MUMU02PG | LODI | 681 | 14141 | 20.7651
[5 empty] | ONMI01CS | ONMI01CS | DELTA | 807 | 28941 | 35.8625
[5 empty] | ONMI02CS | ONMI02CS | DELTA | 807 | 33182 | 41.1177
[5 empty] | ONMI3ACS | ONMI3ACS | DELTA | 807 | 7032 | 8.7138
[5 empty] | ONMI05CS | ONMI05CS | DELTA | 807 | 26335 | 32.6332
[5 empty] | ONMI06CS | ONMI06CS | DELTA | 807 | 24570 | 30.4461
[5 empty] | ONMI07ME | ONMI07ME | DELTA | 807 | 30908 | 38.2999
[5 empty] | ONMI08ME | ONMI08ME | DELTA | 807 | 30658 | 37.9901
[5 empty] | ONMI09CH | ONMI09CH | DELTA | 807 | 30210 | 37.4349
[5 empty] | POCR03CS | POCR03CS | CLEMENTS | 681 | 40476 | 59.4361
[5 empty] | POCR03CS-E | POCR03CS-E | CLEMENTS | 681 | 27838 | 40.8781
[5 empty] | POCR03CS-W | POCR03CS-W | CLEMENTS | 681 | 12638 | 18.558
[5 empty] | POHM01PV | POHM01PV | CLEMENTS | 968 | 14150 | 14.6178
[5 empty] | PPBR03CH | PPBR03CH | CLEMENTS | 622 | 25496 | 40.9904
[5 empty] | PPBR03CH | PPBR03CH-E | CLEMENTS | 622 | 12034 | 19.3473
[5 empty] | PPBR03CH | PPBR03CH-MID | CLEMENTS | 622 | 8666 | 13.9325
[5 empty] | PPBR03CH | PPBR03CH-W | CLEMENTS | 622 | 4796 | 7.7106
[5 empty] | PPCR01ME | PPCR01ME | CLEMENTS | 681 | 22610 | 33.2012
[5 empty] | PPCR02CH | PPCR02CH | CLEMENTS | 681 | 22329 | 32.7885
[5 empty] | PRHZ01CH | PRHZ01CH | DELTA | 566 | 6935 | 12.2527
[5 empty] | PRHZ02PN | PRHZ02PN | DELTA | 691 | 4869 | 7.0463
[5 empty] | PRHZ03PN | PRHZ03PN | DELTA | 691 | 4876 | 7.0564
[5 empty] | PRHZ05CB | PRHZ05CB | DELTA | 454 | 15154 | 33.3789
[5 empty] | PRHZ06CB | PRHZ06CB | DELTA | 519 | 4308 | 8.3006
[5 empty] | PRHZ08CB | PRHZ08CB | DELTA | 519 | 2523 | 4.8613
[5 empty] | PRHZ11CB | PRHZ11CB | DELTA | 660 | 14099 | 21.3621
[5 empty] | PRHZ14CB | PRHZ14CB | DELTA | 660 | 1954 | 2.9606
[5 empty] | PRHZ15CB | PRHZ15CB | DELTA | 660 | 14817 | 22.45
[5 empty] | PRHZ16CB | PRHZ16CB | DELTA | 660 | 4148 | 6.2848
[5 empty] | PRHZ17CB | PRHZ17CB | DELTA | 519 | 3672 | 7.0751
[5 empty] | PRHZ18PS | PRHZ18PS | DELTA | 660 | 6131 | 9.2894
[5 empty] | PRHZ21CH | PRHZ21CH | DELTA | 691 | 6586 | 9.5311
[5 empty] | PRHZ22CB | PRHZ22CB | DELTA | 519 | 2061 | 3.9711
[5 empty] | PRHZ7ASB | PRHZ7ASB | DELTA | 519 | 5292 | 10.1965
[5 empty] | PRHZ7BSB | PRHZ7BSB | DELTA | 660 | 2513 | 3.8076
[5 empty] | PRHZ99MA | PRHZ99MA | DELTA | 660 | 5729 | 8.6803
[5 empty] | PRHZ99CB | PRHZ99CB | DELTA | 660 | 529 | 0.80152
[5 empty] | PRHZ99SB | PRHZ99SB | DELTA | 660 | 1276 | 1.9333
[5 empty] | RING01CS | RING01CS | LODI | 622 | 38947 | 62.6158
[5 empty] | RING01CS | RING01CS-N | LODI | 622 | 19422 | 31.2251
[5 empty] | RING01CS | RING01CS-S | LODI | 622 | 19525 | 31.3907
[5 empty] | RSR101CH | RSR101CH | CLEMENTS | 726 | 19093 | 26.2989
[5 empty] | RSR102CS | RSR102CS | CLEMENTS | 681 | 2540 | 3.7298
[5 empty] | RSR103CH | RSR103CH-DRIVE | CLEMENTS | 566 | 4944 | 8.735
[5 empty] | RSR203CH | RSR203CH | CLEMENTS | 681 | 15807 | 23.2115
[5 empty] | SEJA01CS | SEJA01CS | LODI | 726 | 13156 | 18.1212
[5 empty] | SERA01PN | SERA01PN | LODI | 691 | 12591 | 18.2214
[5 empty] | SLHM01TD | SLHM01TD | LODI | 807 | 15530 | 19.2441
[5 empty] | SLHM02VI | SLHM02VI | LODI | 605 | 11526 | 19.0512
[5 empty] | SLHM03CH | SLHM03CH | LODI | 605 | 11455 | 18.9339
[5 empty] | SLHM05PN | SLHM05PN | LODI | 691 | 15976 | 23.1201
[5 empty] | SLHM06ZN | SLHM06ZN | LODI | 622 | 2790 | 4.4855
[5 empty] | SLHM08PR | SLHM08PR | LODI | 691 | 4940 | 7.1491
[5 empty] | SMSM01ME | SMSM01ME | CLEMENTS | 681 | 15414 | 22.6344
[5 empty] | VKDD01CH | VKDD01CH | LODI | 726 | 18798 | 25.8926
[5 empty] | WHWH01GE | WHWH01GE | DELTA | 691 | 26251 | 37.9899
[5 empty] | WHWH02PG | WHWH02PG | DELTA | 691 | 23900 | 34.5876
[5 empty] | WHWH03AL | WHWH03AL | DELTA | 691 | 20669 | 29.9117
[5 empty] | ZLLAOHCS | ZLLAOHCS | CLEMENTS | 622 | 24736 | 39.7685
[5 empty] | ZLSO01PN | ZLSO01PN | CLEMENTS | 622 | 51248 | 82.3923
[5 empty] | LASHI-CH | LASHI-CH | LODI
[5 empty] | LEWIS-100 | LEWIS-100 | CLEMENTS
[5 empty] | LEWIS-4AC | LEWIS-4AC | CLEMENTS
[5 empty] | LEWIS-18AC | LEWIS-18AC | CLEMENTS
[5 empty] | STARR-HARNEY | STARR-HARNEY | CLEMENTS
[5 empty] | STARR-ZIN | STARR-ZIN | CLEMENTS
[5 empty] | LASHI-ZN | LASHI-ZN | LODI
[5 empty] | SLHM04SB | SLHM04SB | LODI | 622 | 21904 | 35.2154
[5 empty] | MFRN00PN | MFRN00PN | DELTA | 807 | 3709 | 4.596
[5 empty] | DVDU07MC-OLD | DVDU07MC-OLD | DELTA | 545 | 9951
[5 empty] | DVDU07MC-GR | DVDU07MC-GR | DELTA | 545 | 5403
[5 empty] | DVDU05CH | DVDU05CH | DELTA | 871 | 36095 | 42.04